## EXAMPLE Production Schedule
Basic Production Scheduling Template
| COMPANY NAME |  |  |  | START DATE
| Name |  |  |  | 2030-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
| DEPARTMENT |  |  |  | END DATE |  |  | OVERALL PROGRESS |  | PRODUCTION SEQUENCE | [5 empty] | ORDER OF OPERATIONS
| Name |  |  |  | MM/DD/YY |  |  | 20% |  | Description | [5 empty] | Description
| PRODUCT INFORMATION | [9 empty] | QUALITY CONTROL | [10 empty] | SUMMARY
| PRODUCT NAME |  |  |  | SKU |  |  | QUANTITY TO PRODUCE |  |  | INSPECTION POINTS | [10 empty] | NOTES, COMMENTS, ADDITIONAL INFORMATION
| Name |  |  |  | 0 |  |  | 0 |  |  | Description
| DESCRIPTION | [9 empty] | QUALITY CHECKS
| Description | [9 empty] | Description
| RESOURCE ALLOCATION | [9 empty] | PERFORMANCE METRICS
| MACHINE / EQUIPMENT NAME |  |  |  | OPERATOR / TEAM ASSIGNED | [5 empty] | PLANNED OUTPUT
| Name |  |  |  | Name | [5 empty] | Description
| Name |  |  |  | Name | [5 empty] | ACTUAL OUTPUT
| Name |  |  |  | Name | [5 empty] | Description
| Name |  |  |  | Name | [5 empty] | VARIANCE
| Name |  |  |  | Name | [5 empty] | Description
|  |  | PRODUCTS |  |  |  |  | DELIVERABLES |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
| STATUS | PRIORITY | PRODUCT NAMES | OWNER | START DATE | END DATE | # of Days | QUANTITY | % COMPLETE | time axis 2030-03-25 to 2030-08-09
| In Progress | HIGH | PROJECT CATEGORY |  | 2030-03-31 | 2030-04-21 | 15 | 0 | 74.33% | bar: 2030-03-25 to 2030-08-09
| Not Started | MED | Product 1 | Brent W. | 2030-03-31 | 2030-04-03 | 3 | 1 | 33% | bar: 2030-04-01 to 2030-04-03
| Complete | MED | Product 2 | June T. | 2030-04-02 | 2030-04-18 | 13 | 2 | 100% | bar: 2030-04-02 to 2030-04-18
| In Progress | LOW | Product 3 | June T. | 2030-04-13 | 2030-04-18 | 4 | 3 | 90% | bar: 2030-04-15 to 2030-04-18
| In Progress | LOW |  |  | 2030-04-03 | 2030-04-12 | 8 | 4 | 33% | bar: 2030-04-03 to 2030-04-12
| On Hold | LOW |  |  | 2030-04-09 | 2030-04-20 | 9 | 5 | 100% | bar: 2030-04-09 to 2030-04-19
| Needs Review | LOW |  |  | 2030-04-18 | 2030-04-21 | 2 |  | 90% | bar: 2030-04-18 to 2030-04-19
| Needs Update | HIGH | PROJECT CATEGORY |  | 2030-04-22 | 2030-06-23 | 45 |  | 25% | bar: 2030-03-25 to 2030-08-09
| Needs Update | MED | Product 1 | June T. | 2030-04-22 | 2030-06-21 | 45 |  | 70% | bar: 2030-04-22 to 2030-06-21
| In Progress | MED | Product 2 | Kirk C. | 2030-04-30 | 2030-05-02 | 3 |  | 60% | bar: 2030-04-30 to 2030-05-02
| In Progress | MED | Product 3 | Jason D. | 2030-05-05 | 2030-06-19 | 33 |  | 20% | bar: 2030-05-06 to 2030-06-19
| In Progress | MED |  | Seo F. | 2030-05-06 | 2030-06-03 | 21 |  | 0% | bar: 2030-05-06 to 2030-06-03
| In Progress | MED |  |  |  |  | 0 |  | 0%
| In Progress | MED |  |  |  |  | 0 |  | 0%
| In Progress | HIGH | PROJECT CATEGORY |  | 2030-04-14 | 2030-04-25 | 9 |  | 74.33% | bar: 2030-03-25 to 2030-08-09
| In Progress | HIGH | Product 1 | Luiza L. | 2030-04-14 | 2030-04-18 | 4 |  | 33% | bar: 2030-04-15 to 2030-04-18
| In Progress | HIGH | Product 2 | Raghu P. | 2030-04-15 | 2030-04-16 | 2 |  | 100% | bar: 2030-04-15 to 2030-04-16
| In Progress | HIGH | Product 3 | Raghu P. | 2030-04-17 | 2030-04-17 | 1 |  | 90% | bar: 2030-04-17
| In Progress | HIGH |  |  | 2030-04-21 | 2030-04-24 | 3 |  | 33% | bar: 2030-04-22 to 2030-04-24
| In Progress | HIGH |  |  | 2030-04-22 | 2030-04-23 | 2 |  | 100% | bar: 2030-04-22 to 2030-04-23
| In Progress | HIGH |  |  | 2030-04-25 | 2030-04-25 | 1 |  | 90% | bar: 2030-04-25
| In Progress | HIGH |  |  | 0 | 0 | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  | 0 | 0 | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
| In Progress | HIGH |  |  |  |  | 0 |  | 0%
Formulas:
END DATE = MIN([END DATE, row below]:G28)
END DATE = MIN(IF([END DATE, row below]:G42="","",[END DATE, row below]:G42))

## BLANK Production Schedule
Basic Production Scheduling Template
| COMPANY NAME |  |  |  | START DATE
| Name |  |  |  | 2030-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
| DEPARTMENT |  |  |  | END DATE |  |  | OVERALL PROGRESS |  | PRODUCTION SEQUENCE | [5 empty] | ORDER OF OPERATIONS
| Name |  |  |  | MM/DD/YY |  |  | 20% |  | Description | [5 empty] | Description
| PRODUCT INFORMATION | [9 empty] | QUALITY CONTROL | [10 empty] | SUMMARY
| PRODUCT NAME |  |  |  | SKU |  |  | QUANTITY TO PRODUCE |  |  | INSPECTION POINTS | [10 empty] | NOTES, COMMENTS, ADDITIONAL INFORMATION
| Name |  |  |  | 0 |  |  | 0 |  |  | Description
| DESCRIPTION | [9 empty] | QUALITY CHECKS
| Description | [9 empty] | Description
| RESOURCE ALLOCATION | [9 empty] | PERFORMANCE METRICS
| MACHINE / EQUIPMENT NAME |  |  |  | OPERATOR / TEAM ASSIGNED | [5 empty] | PLANNED OUTPUT
| Name |  |  |  | Name | [5 empty] | Description
| Name |  |  |  | Name | [5 empty] | ACTUAL OUTPUT
| Name |  |  |  | Name | [5 empty] | Description
| Name |  |  |  | Name | [5 empty] | VARIANCE
| Name |  |  |  | Name | [5 empty] | Description
|  |  | PRODUCTS |  |  |  |  | DELIVERABLES |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
| STATUS | PRIORITY | PRODUCT NAMES | OWNER | START DATE | END DATE | # of Days | QUANTITY | % COMPLETE | time axis 2030-03-25 to 2030-08-09
|  |  | PROJECT CATEGORY |  | 0 | 0 | 0 | 0 | 0%
|  |  | Product 1 |  |  |  | 0 | 1 | 0%
|  |  | Product 2 |  |  |  | 0 | 2 | 0%
|  |  | Product 3 |  |  |  | 0 | 3 | 0%
[7 empty] | 0 | 4 | 0%
[7 empty] | 0 | 5 | 0%
[7 empty] | 0 |  | 0%
|  |  | PROJECT CATEGORY |  |  |  | 0 |  | 0%
|  |  | Product 1 |  |  |  | 0 |  | 0%
|  |  | Product 2 |  |  |  | 0 |  | 0%
|  |  | Product 3 |  |  |  | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
|  |  | PROJECT CATEGORY |  |  |  | 0 |  | 0%
|  |  | Product 1 |  |  |  | 0 |  | 0%
|  |  | Product 2 |  |  |  | 0 |  | 0%
|  |  | Product 3 |  |  |  | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[5 empty] | 0 | 0 | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
[7 empty] | 0 |  | 0%
Formulas:
END DATE = MIN([END DATE, row below]:G28)

## Dropdown keys - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
STATUS | PRIORITY
Not Started | LOW
In Progress | MED
Complete | HIGH
On Hold
Overdue
Needs Review
Needs Update

## - Disclaimer -
Any articles, templates, or information provided on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.